## Simple Gantt Chart - EX
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[6 empty] | Topic Definition and Framing | [14 empty] | Understanding the Models | [19 empty] | Dataset Design and Experimental Testing | [29 empty] | Analysis & Interpretation | [9 empty] | Writing & Presentation
TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Topic Definition and Framing
1.1 | Literature review | 09/15/25 | 09/27/25 | 12 | 100%
1.2 | Selection of the final research topic | 09/23/25 | 09/27/25 | 4 | 100%
1.3 | Drafting of the problem statement | 09/26/25 | 2025-03-10 | 8 | 100%
2 | Understanding & Setup
2.1 | Deep understanding of AlphaFold2 | 09/30/25 | 2025-11-10 | 11 | 100%
2.1.1 | Study AF2 paper (inputs, Evoformer, structure module, MSA usage) | 09/30/25 | 2025-03-10 | 4 | 100%
2.1.2 | Take detailed notes (inputs, architecture, Evoformer, structure module) | 09/30/25 | 2025-03-10 | 4 | 100%
2.1.3 | Reproduce simple paper | 2025-07-10 | 2025-10-10 | 4 | 100%
2.2 | Deep understanding of AlphaFold3 | 10/13/25 | 10/24/25 | 12 | 100%
2.2.1 | Study AF3 paper (diffusion model, ligands, complexes, MSA changes) | 10/14/25 | 10/17/25 | 4 | 100%
2.2.2 | Take detailed notes | 10/14/25 | 10/17/25 | 4 | 100%
2.2.4 | Compare improvements vs AF2 (diffusion model, complexes, ligands, etc.) | 10/21/25 | 10/24/25 | 4 | 100%
2.3 | Study ESMFold and OmegaFold (language-model-based, no MSA) | 10/21/25 | 10/31/25 | 11 | 100%
3 | Dataset Design and Experimental Testing
3.1 | Selection of a representative protein dataset (diversity in size, fold type, and MSA depth) | 10/28/25 | 2025-07-11 | 11 | 100%
3.1.1 | Justify selection criteria (function, fold type, availability) | 10/28/25 | 10/31/2025 | 4 | 100%
3.3 | Running predictions with AlphaFold3 and comparing results | 2025-04-11 | 11/21/25 | 18 | 100%
3,4 | Run ESMFold and/or OmegaFold predictions (models without MSA) | 2025-11-11 | 11/28/25 | 18 | 100%
3,5 | Collect and compare metrics: pLDDT, RMSD, DockQ, PAE, runtime | 11/25/25 | 2025-06-12 | 11 | 100%
4 | Analysis & Interpretation
4.1 | Compute correlations between MSA depth and model accuracy | 2025-02-12 | 2025-05-12 | 4 | 100%
4.2 | Visualize results (plots, graphs) | 2025-08-12 | 2025-11-12 | 4 | 100%
4.3 | Compare global performance trends between AF2, AF3, ESMFold | 2025-09-12 | 12/17/25 | 4 | 100%
4,4 | Discuss differences and limitations | 12/17/25 | 12/22/25 | 4 | 100%
5 | Writing & Presentation
5,1 | Writing the final report | 12/16/25 | 2026-09-01 | 25 | 100%
5,3 | Preparing the oral presentation slides | 2026-06-01 | 01/16/26 | 11 | 100%